**Timeline for GME-wide initiative**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **AY 2017-2019** | **July** | **Aug** | **Sept** | **Oct** | **Nov** | **Dec** | **Jan** | **Feb** | **Mar** | **Apr** | **May** | **June** |
| Initiative selection | **2017** |  |  |  |  |  |  |  |  |  |  |  |
| Recruitment & QI primer |  |  | **2017** |  |  |  |  |  |  |  |  |  |
| QI primer & initiative development |  |  |  |  | **2017** |  |  |  |  |  |  |  |
| Initiative kick-off |  |  |  |  |  |  | **2018** |  |  |  |  |  |
| PDSA cycles |  |  |  |  |  |  | **2018** |  |  |  |  |  |
| **2018** |  |  |  |  |  | **2019** |  |  |  |  |  |
| Initiative closure & QI day celebration (both years) |  |  |  |  |  |  |  |  |  |  | **2019** |  |

Discussion regarding initiative selection for the next major GME-wide initiative would start in April-June 2019.