# *30-60-90 Plan*

## Narcan Distribution

|  |  |
| --- | --- |
| **Foundations** | |
| **Strengths** | *We have the support of pharmacy and administration* |
| **Barriers** | *Staff concerns about Narcan distribution* |

|  |  |
| --- | --- |
| **Looking Ahead** | |
| **Things to**  **Accomplish in the Next 30 Days** | 1. Meet with pharmacy, ED, OB champion to learn if already participating in DCF Overdose Prevention Project (OPP); if not 2. Check to see if other system hospitals participating in OPP; learn if protocol can be used in this facility; if not 3. Review DCF OPP application form and schedule meeting with ED, pharmacy, and OB champion to discuss proposal and complete and submit OPP application |
| **Things to**  **Accomplish in Next**  **60 Days** | 1. Work with pharmacy to extend distribution to OB floors and complete DCF harm reduction training and staff education or  2. Review protocols used in other system hospitals; meet with ED, pharmacy and OB champion to gain support; revise protocols as necessary for this facility and complete DCF OPP application form, if necessary or  3. Develop protocol for Narcan distribution in appropriate departments and update appropriate systems |
| **Things to**  **Accomplish in Next**  **90 Days** | 1. Track Narcan distribution  2/3. Complete DCF harm reduction training and staff education and implement protocol for Narcan distribution |

Louisiana Department of Health • Office of Public Health • Bureau of Family Health